## Sheet1
Day | Task | Hours | Start Date | End Date
Day 1: Project Setup & Core Infrastructure | - Create a basic Streamlit application skeleton to define the UI structure. | 8 | 2025-06-20 | 2025-06-20
- Configure and test the connection to the OpenAI API for LLM integration.
- Define a list of emotions (e.g., happy, sad, angry) and map them to corresponding colors for visualization.
- Develop an emotion detection function leveraging OpenAI API to analyze user input.
Day 2: Emotion Detection System | - Design an Emotional Quotient (EQ) scoring system with weighted values for different emotions. | 8 | 2025-06-23 | 2025-06-23
- Implement the `update_eq_score()` function to dynamically adjust EQ scores based on detected emotions.
- Test emotion detection accuracy using predefined sample inputs.
- Document the logic and methodology behind emotion detection and EQ scoring.
Day 3: Memory & Context System | - Design a storage system for conversation history (e.g., in-memory or file-based). | 8 | 2025-06-24 | 2025-06-24
- Implement the `remember_everything()` function to store and retrieve conversation data.
- Develop a mechanism to aggregate conversation context for coherent responses.
- Test memory persistence across multiple sessions.
Day 4: Response Generation System | - Develop the `generate_response()` function to produce responses using OpenAI LLM. | 8 | 2025-06-25 | 2025-06-25
- Incorporate full conversation history into response generation for context continuity.
- Design a therapist-like response template to ensure empathetic and supportive tone.
- Embed detected emotion context into responses for personalization.
Day 5: Visualization & Analytics | - Implement tracking of emotion history over time. | 8 | 2025-06-26 | 2025-06-26
- Develop a display for EQ score progress (e.g., line chart or progress bar).
- Create a dataframe to store and analyze emotion frequency.
- Optimize visualization performance for smooth rendering in Streamlit.
Day 6: UI/UX Enhancement | - Design chat message bubbles for a conversational look and feel. | 8 | 2025-06-27 | 2025-06-27
- Implement emotion-based emoji display to reflect user sentiment.
- Add avatars for the user and chatbot to personalize interactions.
- Incorporate responsive design elements for cross-device compatibility.
Day 7: Testing & Debugging | - Test edge cases for emotion detection (e.g., ambiguous or mixed emotions). | 8 | 2025-06-30 | 2025-06-30
- Validate EQ scoring calculations for accuracy.
- Verify memory persistence under various scenarios.
- Test conversation flow for continuity and coherence.
Day 8: Deployment Prep & Documentation | Generate a `requirements.txt` file listing all dependencies. | 8 | 31-06-2025 | 31-06-2025
- Test deployment on Streamlit Cloud as a preliminary step.
- Perform a final quality assurance (QA) check on all features.
- Create comprehensive project documentation, including setup, usage, and maintenance instructions.